CoBo Tasks & Milestones

(Time estimates assume 50% effort of NU & implementation using development kit)

- CoBo Documentation (Nathan Usher)

  - 1st draft  					April 30, 2009  

  - Technical Needs Specification (STB) 	June 1, 2009	

  - Conceptual Design Report 					July 1, 2009

  - Prototype 1 Design Report				October 1, 2009

  - Prototype 1 Test Report			January 1, 2010

  - Prototype 2 Design Report				February 1, 2010

  - Prototype 2 Test Report			June 1, 2010

  - Production Readiness Report			June 1, 2010

- Firmware Development

  - Microprocessor memory space (Nathan Usher)

    - Must be defined to allow software development to begin

- Done

  - High speed data readout (Nathan Usher – 70% complete)

    - Implementation of segmented pipeline (1wk)

    - Zero suppression & Time stamping (1wk)

    - Built in flexibility for additional pipeline steps

      - Zip compression (future)

- Peak fitting algorithms (future)

      - Base-line correction (future)

      - Pile-up recognition (future)

      - Constant-Fraction algorithms (future)

      - etc

  - Double buffer DDR2 SDRAM (Nathan Usher, 1 month code & test)

- Firmware interface with SD chip (80% complete)

    - Switching mechanism between SD-RAM chips

      - Not possible w/ starter kit bc need 2 chips

      - Must be completed when prototype available

  - Packet creation (Nathan Usher, 1 month code)

    - Implement TCP packets in firmware

- Checksum

      - Packet size definition

    - Define substructure of packet

      - Header

      - Data ordering

  - Microprocessor software (schedule assumes work completed at Saclay w/ 1 month implementation in CoBo)

    - VxWorks selected as OS (Done)

    - Implement debug feature, Reliability (Embedded Hypervison,!)

    - Emulators: where do these come in?

    - Reading & slow controls packets

    - Acknowledge high speed data transmission

    - Monitoring features

      - Voltage

      - Temperature

      - Current

      - Numeric error counts (how do you fit this in?)

      - Etc

    - Fast/slow controls

      - Needs requirements defined

- Hardware (Nathan Usher)

  - Component Selection

    - FPGA

      - Delay finalizing until after prototype 1

      - Use 1136 pin Virtex5 line

      - Confirm selection, Jan 1, 2010

      - w/ Shebli

    - Clock Chip

      - Determine number required

        - 1 for SCA write (freq depends on expt)

        - Do separate clocks need to be sent to the ADC and the SCA read? (freq = 25 MHz)

      - Done

    - RAM chip

      - Confirm chip selected is appropriate.

      - Is extra RAM required for processor or is enough block memory available already?

      - Need to know from software group the size of the compiled software.

      - Done

    - ROM chip

      - Two required

      - Use ROM from Xilinx that matches FPGA

      - Confirm selection with software group

      - Done

    - Ethernet interface

      - If using 1 Gbit Ethernet copy from development kit

      - If using 10 Gbit Ethernet research required

      - Assume 64 chan/AGET & 4 AGET/ASAD

      - Requires decision regarding uTCA vs NIM

    - Development kit modifications

      - RAM daughter card

      - Time required?

  - Interface Definition (completed by July 1, 2009)

    - IDR Mutant

      - Add sync signal

      - Confirm connectors w/ Gilles, sent email May 4th

    - IDRASAD

      - Confirm slow controls & data transmitted of same cable

      - Confirm connectors w/ Jerome, sent email May 4th

    - IDRSwitch

      - Who will be handling this?

        - Point of discussion  JLP please program

  - Board Schematics (4wks)

  - Board Layout (8wks)

  - Finalize number of CoBos to be produced (April 1, 2010)