## Sheet1
Equipment
order | urgency | action | who | when | comments
0 | medium | Prepare tool box list and order | Moshe + Tamas | 2016-12-22
0 | high | Non nylon tubing for both detectors | Moshe | 2016-12-22
0 | high | Cables from small HV to MM sma | Moshe | 12//22/2016
0 | high | Modify field cage dimensions | Tamas | 2016-12-22
0 | high | Order new gas if needed | Moshe | 12//22/2016 | Update Remco and Dave
0 | high | Prepare copper holder for MM preamp | Chris | 2017-01-15 | Patrick
0 | high | Order heaters for baking | Moshe | 2016-12-22
0 | high | Protecting pancake cathode HV | Chris | - | Ask Cern
0 | high | Prepare source holder for pancake | ?
2 | high | Making/buying filter for mesh | Tamas | 2017-01-07
3 | low | Order additional MM board | Chris | -
6 | low | Making/buying filter for detector cathode | - | 2017-02-15
0 | high | Repair cathode Cu-Be contact | Moshe | 2017-01-07
Lab
order | urgency | action
1 | high | Install MM in pancake | Moshe | 2016-12-29
0 | high | Pressure test of chamber | Moshe | 2017-01-15 | Decide on procedure
0 | high | Baking of chamber (?) | - | - | Disscuss with Lolly the procedure of this
0 | medium | Glue additional field cage | Tamas
1 | high | Measure mesh capacity | Tamas | 22/12/2016
1 | high | Characterize mesh noise | Moshe | 2017-01-08
1 | high | Vacuum test of chamber | Moshe | 2017-01-15
2 | high | Quality tests on pancake | Moshe | 2017-01-27
3 | high | Clean all possible parts | Chris | 2017-01-15
4 | high | Assemble proton detector | - | 2017-02-03
5 | medium | Quality tests on detector | - | 2017-02-10
Other
order | urgency | action
0 | high | Check gas options
0 | high | Find clean room | Chris | 2016-12-19
0 | medium | Write gain code | Moshe | 2017-01-20
0 | mediun | Writing first assembly summary | Moshe | 2017-12-30
0 | high | Assembly/disassmebly instructions | Moshe | 2017-12-30
1 | high | conclude GHS scheme | Tamas | 2017-12-30
2 | medium | prepare control scheme | Tamas | 2017-12-30
6 | low | writing NIM paper | - | -
6 | low | Writing PAC | Chris | -
? | low | degrader (everything) | - | -
? | low | detector support | - | -
0 | high | calculate collimator thickness | Moshe | 22/12/2017
0 | high | Prepare gating grid | Tamas | 2017-02-28 | Need to finish the design and test it
0 | medium | Calculate effect of drifting distance | Moshe | 2017-01-20